## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | RESPONSIBILITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Class User entity code | John Pierre | 1 | 6
Class Branch managerentity code | Lilian | 1 | 6
Class Client entity code | Shadi | 1 | 6
Class Corporation manager entity code | Nour | 1 | 6
Class Cart entity code | John Pierre | 1 | 6
Class Item entity code | Lilian | 1 | 6
Class Catalog entity code | Shadi | 1 | 6
Class Branch entity code | Nour | 1 | 6
Class Complain entity code | John Pierre | 1 | 6
Class Report entity code | Lilian | 1 | 6
Class Order Report entity code | Shadi | 1 | 6
Class Income Report entity code | Nour | 1 | 6
Class Complain Report entity code | John Pierre | 1 | 6
Feedback on every thing | Everyone | 7 | 1
Design SysManager GUI | John Pierre | 8 | 10
Design Worker GUI | Lilian | 8 | 10
Design ServiceW GUI | Shadi | 8 | 10
Design BranchManager GUI | Nour | 8 | 10
Design ClientAccount GUI | John Pierre | 8 | 10
Design ShipPay GUI | Lilian | 8 | 10
Design Cart GUI | Shadi | 8 | 10
Design ItemShowCatalog GUI | Nour | 8 | 10
Design ItemUpdate GUI | John Pierre | 8 | 10
Design ItemCart GUI | Lilian | 8 | 10
Design ItemCatalog GUI | Shadi | 8 | 10
Design Complain GUI | Nour | 8 | 10
Design Catalog GUI | John Pierre | 8 | 10
Design Report GUI | Lilian | 8 | 10
Design SystemLog GUI | Shadi | 8 | 10
Design CorporationManager GUI | Nour | 8 | 10
Feedback on every thing | Everyone | 18 | 1
Coding SysManager Controller | John Pierre | 19 | 16
Coding Worker Controller | Lilian | 19 | 16
Coding ServiceW Controller | Shadi | 19 | 16
Coding BranchManager Controller | Nour | 19 | 16
Coding ClientAccount Controller | John Pierre | 19 | 16
Coding ShipPay Controller | Lilian | 19 | 16
Coding Cart Controller | Shadi | 19 | 16
Coding ItemShowCatalog Controller | Nour | 19 | 16
Coding ItemUpdate Controller | John Pierre | 19 | 16
Coding ItemCart Controller | Lilian | 19 | 16
Coding ItemCatalog Controller | Shadi | 19 | 16
Coding Complain Controller | Nour | 19 | 16
Coding Catalog Controller | John Pierre | 19 | 16
Coding Report Controller | Lilian | 19 | 16
Coding SystemLog Controller | Shadi | 19 | 16
Coding CorporationManager Controller | Nour | 19 | 16
Feedback on every thing | Everyone
Testing and debugging | Everyone | 35 | 10